## Villa
Types | Codes | Descriptions | Durations | Predecessors
Gate | Start
Task | A.1 | Building Design | (6, 12, 18) | Start
Task | A.2 | Electrical Design | (3, 6, 9) | A.1
Task | A.3 | Plumbing Design | (3, 6, 9) | A.1
Task | A.4 | Fire System Design | (2, 4, 6) | A.1
Task | B.1 | Signing Project Contract | (2, 4, 6) | A.2, A.3, A.4
Task | B.2 | Project Permit | (3, 6, 9) | B.1
Task | B.3 | Electrical Permit | (4, 8, 12) | B.1
Task | B.4 | Plumbing Permit | (3, 6, 9) | B.1
Task | C.1 | Installation of Mobilization Building | (4, 8, 12) | B.2, B.3, B.4
Task | C.2 | Road Work | (3, 6, 9) | C.1
Task | C.3 | Fence Work | (2, 4, 6) | C.1
Task | D.1 | Clearing and Grubbing | (2, 4, 6) | C.2, C.3
Task | D.2 | Excavation | (6, 12, 18) | D.1
Task | D.3 | Filling | (10, 20, 30) | D.2
Task | E.1 | Pile | (9, 18, 27) | D.3
Task | E.2 | Concrete | (10, 20, 30) | E.1
Task | E.3 | Raft Foundation | (15, 30, 45) | E.1
Task | F.1 | Column and Curtain Wall | (8, 16, 24) | E.2, E.3
Task | F.2 | Slab | (3, 6, 9) | F.1
Task | F.3 | Slab Insulation | (6, 12, 18) | F.1
Task | F.4 | Masonry | (3, 6, 9) | F.1
Task | F.5 | Upper Slab | (2, 4, 6) | F.1
Task | G.1 | Column and Curtain Wall | (4, 8, 12) | F.2, F.3, F.4, F.5
Task | G.2 | Slab | (4, 8, 12) | G.1
Task | G.3 | Slab Insulation | (3, 6, 9) | G.1
Task | G.4 | Masonry | (2, 4, 6) | G.1
Task | G.5 | Upper Slab | (2, 4, 6) | G.1
Task | H.1 | Roof Beam Installation | (4, 8, 12) | G.2, G.3, G.4, G.5
Task | H.2 | Roof Installation | (4, 8, 12) | H.1
Task | H.3 | Roof Isolation | (2, 4, 6) | H.1
Task | I.1 | Installation of Electric | (6, 12, 18) | H.2, H.3
Task | I.2 | Installation of Plumbing | (4, 8, 12) | H.2, H.3
Task | I.3 | Installation of Fire System | (2, 4, 6) | H.2, H.3
Task | J.2 | Interior Brick Wall | (16, 32, 48) | I.1, I.2, I.3
Task | J.3 | Exterior Brick Wall | (14, 28, 42) | I.1, I.2, I.3
Task | J.1 | Drywall | (9, 18, 27) | J.2, J.3
Task | K.1 | Plaster (ext-int) | (9, 18, 27) | J.1
Task | L.1 | Travertine Coating | (14, 28, 42) | K.1
Task | L.2 | Marble Coating | (8, 16, 24) | K.1
Task | L.3 | Tile Mosaic Coating | (4, 8, 12) | K.1
Task | L.4 | Ceramic Coating | (2, 4, 6) | K.1
Task | L.5 | Epoxy | (2, 4, 6) | K.1
Task | L.6 | Suspended Ceiling Cover | (8, 16, 24) | K.1
Task | L.7 | Outer Wall Covering | (12, 24, 36) | K.1
Task | M.1 | Fenestration Installation | (3, 6, 9) | L.1, L.2, L.3, L.4, L.5, L.6, L.7
Task | M.2 | Wood Work | (6, 12, 18) | M.1
Task | M.3 | Aluminium Joinery | (4, 8, 12) | M.1
Task | M.4 | Metal Joinery | (3, 6, 9) | M.1
Task | N.1 | Interior Paint | (4, 8, 12) | M.2, M.3, M.4
Task | N.2 | Exterior Paint | (9, 18, 27) | N.1
Task | O.1 | Ventilation System | (2, 4, 6) | N.2
Task | O.2 | Clean-Waste Water | (6, 12, 18) | N.2
Task | O.3 | Rain Water | (2, 4, 6) | N.2
Task | O.4 | Mechanical Automation | (2, 4, 6) | O.1, O.2, O.3
Task | O.5 | Mechanical Electric Work | (2, 4, 6) | O.1, O.2, O.3
Task | P.1 | Fire Protection System | (2, 4, 6) | O.4, O.5
Task | P.2 | Fire Detection System | (3, 6, 9) | O.4, O.5
Task | P.3 | Security Lighting | (2, 4, 6) | O.4, O.5
Task | Q.1 | Cleaning | (2, 4, 6) | P.1, P.2, P.3
Task | Q.2 | Final Control | (2, 4, 6) | Q.1
Task | Q.3 | Delivery | (1,1,1) | Q.2
Gate | Completion |  |  | Q.3